# ONE2CALL MSA REVIEW — WORK PLAN

Date: 9 December 2025

Client: One2Call Limited

Document: MSA Defined Services (HJ7) and Maintenance Schedule (HJ1)

# EXECUTIVE SUMMARY

The One2Call MSA is well-structured with strong pro-supplier provisions. The core terms are substantially complete and require only targeted amendments. The main work is to complete the service schedules, add exit/transition provisions, and create an optional security schedule for cyber security services.

Work is divided into Phase 1 (immediate completion of MSA) and Phase 2 (additional templates and detailed service schedules).

# PHASE 1: MSA COMPLETION

## 1.1 Critical Drafting Fixes

(a) Correct Schedule numbering — The Terms and Conditions are headed "Schedule 2" but should be "Schedule 1" per the cover document structure. Correct this inconsistency.

(b) Add "Data Protection Legislation" definition — This term is used in clause 18.1 but not defined. Add definition to clause 1 referencing UK GDPR and EU GDPR.

## 1.2 Expand Clause 21 (Consequences of Termination)

Add exit/transition provisions covering:

(a) Customer data extraction right — Customer may request return or deletion of Customer Data within 30 days of termination.

(b) Transition assistance — Supplier to provide reasonable transition assistance for up to 3 months at Supplier's then-current rates.

(c) Data deletion certification — Following data return, Supplier to confirm deletion of Customer Data (subject to legal retention requirements).

(d) Equipment — Customer equipment to be returned; Supplier equipment to be collected or purchased at net book value.

## 1.3 Clarify Indemnity Cap

Add to clause 19.4: "The liability of either party under clause 17 (Indemnities) shall be subject to the cap set out in this clause 19.4."

## 1.4 Draft Security Schedule (Schedule 4)

Create optional Security Schedule to be incorporated by reference in Orders that include cyber security services. Key areas:

(a) Security standards compliance — ISO 27001 certification, Cyber Essentials Plus accreditation, compliance obligations.

(b) Incident definitions — Define Incident, Known Vulnerability, Latent Vulnerability, Virus, and Mitigate.

(c) Incident handling procedures — Detection, escalation, response, resolution, post-incident review.

(d) Vulnerability management — Scanning, patching, remediation timelines.

(e) Business continuity/disaster recovery — DR plan, testing, RTO/RPO commitments.

(f) Notification obligations — Timing and content of security incident notifications to Customer.

## 1.5 Draft Schedule 3 Service Schedules (Framework)

Create modular service schedule framework. Detail to be completed in Phase 2.

Schedule 3A: Managed IT Services

Key areas: Service scope (device management, infrastructure monitoring, helpdesk support, backup and recovery, release management, administration); Service exclusions; Customer obligations (access, cooperation, acceptable use); SLAs (response times by priority P1-P4, uptime targets); Service credits; Reporting.

Schedule 3B: Cyber Security Services

Key areas: Service scope (threat detection and response, firewall and network security, vulnerability management, security awareness training, email and web security, compliance support); Incorporates Schedule 4 (Security Schedule); Customer security obligations; Incident response SLAs; Limitations (no guarantee against all threats); Third-party tool dependencies.

Schedule 3C: Cloud Management

Key areas: Service scope (Microsoft 365 administration, Azure management, cloud backup, cloud security configuration, licence management, migration services); Subscription/licence ownership (Customer owns); Third-party platform terms (Microsoft, etc.); Data residency; SLAs (response times, excludes underlying platform outages); Optimisation recommendations.

Schedule 3D: Connectivity

Key areas: Service scope (business broadband, leased lines, network management, Wi-Fi solutions, hybrid workforce connectivity); Circuit specifications; Installation and provisioning; Uptime targets; Carrier/third-party dependencies; IP address allocation; Equipment (routers, firewalls); Service credits for downtime.

Schedule 3E: Telecoms

Key areas: Service scope (3CX VoIP phone systems, Microsoft Teams Voice, mobile device management, SIP trunking, number porting); System configuration and training; Handset provision; Call recording (ownership, retention); Number ownership (Customer retains ported numbers); Carrier dependencies; SLAs (system availability, fault response); Acceptable use.

Schedule 3F: Hardware Provision and Maintenance

Key areas: Incorporates Maintenance Schedule (HJ1); Equipment list and specifications; Preventative, corrective, and emergency maintenance; Response and fix times; Spare parts (charging, ownership); Excluded causes (misuse, environment, third-party interference); Customer obligations (access, operating conditions); End-of-life and disposal.

## 1.6 Attach Maintenance Schedule to MSA

Incorporate Maintenance Schedule (HJ1) as an annex to Schedule 3F or as a standalone Schedule 5, cross-referenced from the MSA. Update MSA cover document to list Maintenance Schedule in schedule list.

## 1.7 Add Regulatory Compliance Clauses

Add clauses to clause 24 (General) with explanatory drafting notes:

(a) Anti-bribery — Compliance with Bribery Act 2010; no bribes or facilitation payments; right to terminate for breach. [Note: May be required by larger clients and public sector customers.]

(b) Anti-slavery — Compliance with Modern Slavery Act 2015; due diligence on supply chain; annual statement. [Note: May be required by larger clients and public sector customers.]

(c) Dispute escalation — Before commencing litigation, disputes to be escalated to senior management for good faith resolution discussions for 14 days. [Note: May reduce legal costs and preserve commercial relationships.]

# PHASE 2: ADDITIONAL TEMPLATES AND DETAILED SCHEDULES

## 2.1 Systems Integration / Project SOW Template

Create SOW template for project-based work (migrations, infrastructure deployments, consultancy) based on Systems Integration Agreement precedent. Key areas:

(a) Project scope and deliverables; (b) Milestones and timeline; (c) Acceptance testing procedures; (d) Change control procedure; (e) Payment milestones; (f) Project-specific IP provisions (if bespoke work); (g) Go-live and handover.

## 2.2 Complete Service Schedule Detail

Populate full detail for each Schedule 3 sub-schedule (3A-3F) including: Detailed service descriptions aligned to One2Call website offerings; Specific SLA metrics (response times, fix times, uptime percentages); Service credit calculations; Pricing structure frameworks; Standard exclusions and customer obligations.

## 2.3 Order Form Template

Review and update Order Form template to work with new schedule structure. Ensure Order Form captures: Selected services (by reference to Schedule 3 sub-schedules); Service-specific details and configurations; Pricing and payment terms; Start date and initial term; Any deal-specific variations.

# REFERENCE DOCUMENTS

Client Documents:

• One2call - 2025 Templates - MSA Defined Services - HJ7.docx

• One2call - 2025 Templates - Maintenance Schedule - HJ1.docx

Precedents:

• Managed services agreement (1).docx — Primary reference for exit provisions, security schedule, service schedules

• Hardware maintenance agreement (1).docx — Reference for Schedule 3F and Maintenance Schedule alignment

• Systems integration agreement (pro-supplier) (1).docx — Reference for Phase 2 SOW template

• Software maintenance_ service level agreement.docx — Reference for SLA structure and service credits